## Sheet1
Android Training (1 week : 20/8 →26/8 – 5 days) 27/8: review
2h→0.25day 4h→0.5day ; 8h→1day
| No | Name | Descriiption |  | Estimate Time | Status
| 1 | Java Conventions |  |  | 2-3h |  | Chốt 24/8 xong
| 2 | Activity, lauch mode Theme |  |  | 2-3h
| 3 | Fragment |  |  | 2-3h
| 4 | Service | Các loại service, dùng khi nào |  | 2-3h
| 5 | Thread, AsysTask |  |  | 2-3h
| 6 | Layout |  |  | 2-3h
| 7 | ListView, RecycleView, ViewPager, Tag | Ưu, nhược điểm |  | 2-3h
| 8 | SQLite |  |  | 2-3h
| 9 | Animation |  |  | 2-3h |  |  | 24/8 → 26/8: code sample 27/8: review
| 10 | Dialog |  |  | 2-3h
11
12
13
[Evaluation] https://docs.google.com/spreadsheets/d/1EIFoFJCHsiqpWFUn4mkBmC945CsrUbjj-_nJ5sg-gWs/edit#gid=5 Preview [List of Android Advance 1] "- Installing environment + Download Eclipse, Android SDK + Install plugin for eclipse + SDK, AVD Management (update, create, start a virtual device)" - Learn about Android architecture - Learn about basic components of an Android application "- Create HelloWorld project, learn about folders and files in project: + Folders: src,lib, asset, res... + xml files, especially AndroidMenifest.xml " "- Resource + Learn about resources in Android http://developer.android.com/guide/topics/resources/available-resources.html " "- Activity: + Concept, lifecycle of an activity + Defining an activity in AndroidManifest + Implicit Intent and Explicit Intent + How to start an Activity: startActivity and startActivityForResult + Pass data between two activities " "- UI layout: + FrameLayout + LinearLayout + RelativeLayout + GridLayout + TableLayout " "- UI Controls: + TextView + EditText + ImageView + Button + ImageButton + ToggleButton + RadioButton + RadioGroup + ListView + GridView + ScrollView + Menu " "- Event Handling + Create listener, registration listener + Some popularListener: OnClickListener, OnTouchListener, OnItemClickListener..." "- Animation: + Some animations: TranslateAnimation, AlphaAnimation, RotateAnimation... " "- Database: + Learn about SQLite in Android + How to create database, table + Query: insert, update, delete" "- Some other components: + ContentProvider + Service + Reciever" "- Some other issues: + Display message using Toast + AlertDialog: how to use, how to custom + Dialog + PopupWindow " "- Thread + AsynTask + Handler + Thread" "- Fragment + Viewpager + Fragment"